## October 2025
PACT Monthly Coverage tracker WFP TPM
Type of Monitoring | Kassala Hub |  |  | Kosti Hub |  |  | Forchana Hub |  |  | Dongola Hub |  |  | Country Office (CO) |  |  | CO Overall
| P | A | % | P | A | % | P | A | % | P | A | % | P | A | % | P | A | %
DM: | 15 | 12 | 80% | 95 | 56 | 58.95% | 9 | 9 |  | 10 | 10 | 100% | 22 | 19 | 86.36% | 151 | 106 | 70.2%
GFA In-Kind | 15 | 12 | 80% | 95 | 56 | 58.95% | 9 | 9 |  | 10 | 10 | 100% | 17 | 14 | 82.35% | 146 | 101 | 69.18%
GFA CBT | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 5 | 5 |  | 5 | 5
e-BSFP | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0!
PDM | 0 | 0 |  | 24 | 9 | 37.5% | 20 | 20 | 100% | 0 | 0 |  | 0 | 0 |  | 44 | 29 | 65.91%
AM: | 333 | 274 | 82.28% | 232 | 150 | 64.66% | 74 | 74 | 100% | 34 | 32 | 94.12% | 48 | 48 | 100% | 721 | 578 | 80.17%
TSFP | 333 | 274 | 82.28% | 230 | 148 | 64.35% | 74 | 74 | 100% | 34 | 32 | 94.12% | 48 | 48 | 100% | 719 | 576 | 80.11%
PSN | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0!
FFA | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
SF | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | #DIV/0!
THR | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0!
PHL | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
MDM | 0 | 0 | #DIV/0! | 17 | 17 |  | 3 | 3 |  | 10 | 10 | 100% | 14 | 14 | 100% | 44 | 44 | 100%
Warehouse |  |  |  | 0 | 0 | #DIV/0! | [9 empty] | 0 | 0 | #DIV/0!
RPME | 0 | 0 | 0% | 0 | 0 | 0% | 40 | 40 | 100% | 0 | 0 | 0% | 0 | 0 | 0%
Hot meal Khartoum | [12 empty] | 0 | 0 |  | 0 | 0 | #DIV/0!
SO3 OM 480
Post Harvest
Total | 348 | 286 | 82.18% | 368 | 232 | 63.04% | 146 | 146 | 100% | 54 | 52 | 96.3% | 84 | 81 | 96.43% | 960 | 757 | 78.85%
Type of Monitoring | Total Plan | Total Actual | Total Actual |  | 1. Fill the cells in White.
DM: | 151 | 106 | 70.2% |  | 2. Take note of each activity that used the wrong tools as we agreed.
GFA In-Kind | 146 | 101 | 69.18% |  | 3. Highlight the sites which need more clarification or adjustments in yellow in the raw data file.
GFA CBT | 5 | 5 |  |  | 4. Fill out the sites and activities for each enumerator in the Second sheet fees).
e-BSFP | 0 | 0 | #DIV/0! |  | 5. For PDM take note of if the sites have less than 5 questionnaires (take note of that and mark it in yellow)
PDM | 44 | 29 | 65.91% |  | 6. Ensure to count the sites from Column (T) and cross-check with Column ®
AM: | 721 | 578 | 80.17% |  | 7. Also for GFA and Market Diviersion take note(Count) of each sites how many questionnaires
TSFP | 719 | 576 | 80.11%
PSN
FFA
SF
THR
PHL
MDM | 44 | 44 | 100%
Warehouse | 0 | 0 | #DIV/0!
RPME | 0 | 0
Hot meal Khartoum | 0 | 0
DM SEWPP | 0 | 0
Total | 960 | 757 | 78.85%
Type of Monitoring | Kassala Hub | [14 empty] | CO Overall |  |  | Done
| AL Gazira State |  |  | Blue Nile State |  |  | Gadarif State |  |  | Kassala State |  |  | Sennar State
| P | A | % | P | A | % | P | A | % | P | A | % | P | A | % | P | A | %
DM: | 3 | 3 |  | 1 | 0 |  | 7 | 7 |  | 4 | 2 | 50% | 0 | 0 |  | 15 | 12 | 80%
GFA In-Kind | 3 | 3 | 100% | 1 | 0 | 0% | 7 | 7 | 100% | 4 | 2 | 50% | 0 |  |  | 15 | 12 | 80%
GFA CBT
e-BSFP
PDM | [15 empty] | 0 | 0 | #DIV/0!
AM: | 103 | 99 | 96.12% | 33 | 23 | 69.7% | 57 | 54 | 94.74% | 41 | 34 | 82.93% | 99 | 64 |  | 333 | 274 | 82.28%
TSFP | 103 | 99 | 96.12% | 33 | 23 | 69.7% | 57 | 54 | 94.74% | 41 | 34 | 82.93% | 99 | 64 | 64.65% | 333 | 274 | 82.28%
PSN
FFA
SF
THR
PHL
MDM | [15 empty] | 0 | 0 | #DIV/0!
Warehouse | [15 empty] | 0 | 0 | #DIV/0!
RPME
Total | 106 | 102 | 96.23% | 34 | 23 | 67.65% | 64 | 61 | 95.31% | 45 | 36 | 80% | 99 | 64 | 64.65% | 348 | 286 | 82.18%
|  |  |  | 11 oct 10 nov | PDM ND 30Q | [5 empty] | PDM 5Q |  |  | PDM 5 SITES 75Q
Type of Monitoring | Kosti Hub | [20 empty] | CO Overall
| East Darfur State |  |  | North Darfur State |  |  | North Kordofan State |  |  | South Darfur |  |  | South Kordofan State |  |  | West Kordofafn State |  |  | White Nile State
| P | A | % | P | A | % | P | A | % | P | A | % | P | A | % | P | A | % | P | A | % | P | A | %
DM: | 36 | 36 |  | 10 | 5 | 50% | 1 | 1 | 100% | 13 | 6 | 46.15% | 15 | 4 | 26.67% | 16 | 0 |  | 4 | 4 |  | 95 | 56 | 58.95%
GFA In-Kind | 36 | 36 | 100% | 10 | 5 | 50% | 1 | 1 | 100% | 13 | 6 | 46.15% | 15 | 4 | 26.67% | 16 | 0 | 0% | 4 | 4 | 100% | 95 | 56 | 58.95%
GFA CBT
e-BSFP
PDM |  |  | #DIV/0! | 14 | 3 | 21.43% |  |  |  | 2 | 1 | 50% | 8 | 5 | 62.5% |  |  | #DIV/0! |  |  |  | 24 | 9 | 37.5%
AM: | 0 | 0 | #DIV/0! | 28 | 20 | 71.43% | 13 | 7 | 53.85% | 52 | 40 | 76.92% | 71 | 41 | 57.75% | 39 | 14 | 35.9% | 29 | 28 | 96.55% | 232 | 150 | 64.66%
TSFP |  |  | #DIV/0! | 26 | 18 | 69.23% | 13 | 7 | 53.85% | 52 | 40 | 76.92% | 71 | 41 | 57.75% | 39 | 14 | 35.9% | 29 | 28 | 96.55% | 230 | 148 | 64.35%
PSN |  |  |  | 2 | 2
FFA
SF
THR
PHL
MDM |  |  |  | 9 | 9 | 100% | 1 | 1 | 100% | 3 | 3 | 100% | [6 empty] | 4 | 4 | 100% | 17 | 17 | 100%
Warehouse | [21 empty] | 0 | 0 | #DIV/0!
RPME
Total | 36 | 36 | 100% | 61 | 37 | 60.66% | 15 | 9 | 60% | 70 | 50 | 71.43% | 94 | 50 | 53.19% | 55 | 14 | 25.45% | 37 | 36 | 97.3% | 368 | 232 | 63.04%
Type of Monitoring | Forchana Hub | [5 empty] | CO Overall |  |  | Done
| West Darfur |  |  | Central Darfur
| P | A | % | P | A | % | P | A | % |  | 11 October till 10 November 2025 all activies
DM: | 0 | 0 | #DIV/0! | 9 | 9 | 100% | 9 | 9 | 100% |  |  | 11.1
GFA In-Kind |  |  | #DIV/0! | 9 | 9 | 100% | 9 | 9 | 100% |  |  | 109 | 103 | 6 no6 active TSFP
GFA CBT
e-BSFP
PDM | 20 | 20 |  |  |  | #DIV/0! | 20 | 20 | 100% |  | 191 wd q
AM: | 22 | 22 | 100% | 52 | 52 | 100% | 74 | 74 | 100%
TSFP | 22 | 22 | 100% | 52 | 52 | 100% | 74 | 74 | 100%
PSN
FFA
SF
THR
PHL
MDM |  |  |  | 3 | 3 | 100% | 3 | 3 | 100%
Warehouse
RPME | 40 | 40 | 100% |  |  |  | 40 | 40 | 100%
Total | 82 | 82 | 100% | 64 | 64 | 100% | 146 | 146 | 100%
Type of Monitoring | Dongola Hub | [5 empty] | CO Overall |  |  | Done
| Northen State |  |  | Revier Nile State
| P | A | % | P | A | % | P | A | %
DM: | 0 | 0 | #DIV/0! | 10 | 10 | 100% | 10 | 10 | 100%
GFA In-Kind |  |  | #DIV/0! | 10 | 10 | 100% | 10 | 10
GFA CBT
e-BSFP
PDM
AM: | 9 | 7 | 77.78% | 25 | 25 | 100% | 34 | 32 | 94.12%
TSFP | 9 | 7 | 77.78% | 25 | 25 | 100% | 34 | 32 | 94.12%
PSN
FFA
SF
THR
PHL
MDM |  |  |  | 10 | 10 |  | 10 | 10 | 100%
Warehouse
RPME
Post Harvest
Total | 9 | 7 | 77.78% | 45 | 45 | 100% | 54 | 52 | 96.3%
6 - 5 Nove DM 7-15 Nov
Type of Monitoring | Country Office (CO) | [5 empty] | CO Overall |  |  | Done
| Red Sea State |  |  | Khartoum State
| P | A | % | P | A | % | P | A | %
DM: | 5 | 5 | 100% | 17 | 14 | 82.35% | 22 | 19 | 86.36%
GFA In-Kind |  |  | #DIV/0! | 17 | 14 | 82.35% | 17 | 14 | 82.35% |  | 4 Nov- 13 Nov
GFA CBT | 5 | 5 |  |  |  |  | 5 | 5 | 100%
e-BSFP | [6 empty] | 0 | 0 | #DIV/0!
PDM
AM: | 40 | 40 | 100% | 8 | 8 | 100% | 48 | 48 | 100%
TSFP | 40 | 40 | 100% | 8 | 8 | 100% | 48 | 48 | 100%
PSN
FFA
SF
THR
PHL
MDM |  |  |  | 14 | 14 | 100% | 14 | 14 | 100%
Warehouse
RPME
Hot meal Khartoum
Total | 45 | 45 | 100% | 39 | 36 | 92.31% | 84 | 81 | 96.43%
| State | oct | NOV
| Gadaref | 11 | 15
| kass | 19 | 11
| BN | 16 | 5
| GZ | 11 | 10
| Sinnar | 19 | 16
GFA | Dongla | 6 | 10
AIM | Dongla | 6 | 5